## Projects
Trustee Planning and Budget Tool
Last Updated
[15 empty] | 0 | 0 |  |  |  | 1700
Facility | Room/Location | Project Title | Major Maintenance/ Project | Proposed Completed Year | Budget Year | Initiation | Why (life safety, maintenance, beyond useful life, improvement, wish list) | Initial Comments | Priority | Risk/impact | Urgency | Plan & Budget | Description of Proposed Work | Budget Note | Estimated cost | Actual Cost | Planning year | Funding Source | Budgeted Account # | Endowment Used | Resource Committee approved | Status | Completion Date | Final Description of What Was Done
Dawes | Install fire extinguishers |  |  | 2018 | 2018 |  | Life safety - Chuck to purchase | funded from remaining funds in maintenance budget | 25 | 5 | 5 |  |  |  | 500 |  | na |  |  |  |  | Done | 2018
Dawes | Kitchen dishwasher | Replace dishwasher |  | 2018 | 2018 |  | Beyond Useful Life -Current unit installed in 2004 is not functioning properly, doesn't not get dishes clean and top rack cannot be used - Decision to use remaining 2018 budget to replace unit | funded from remaining funds in maintenance budget | 25 | 5 | 5 |  |  |  | 400 |  | na |  |  |  |  | Done | 2018
Elm Court | Bathroom | Replace wall heater |  | 2018 | 2018 |  | Beyond Useful Life - Current unit is 4000 BTU - new unit has already been purchased; need to update wiring to enable replacement of unit | Bathroom currently has no heat, needs to be replaced now; accurate estimate challenging (walls may have to be opened to run an appropriate 220 V line from the heater to the panel | 25 | 5 | 5 |  |  |  | tbd |  | na |  |  |  |  | Done | 2018
Brainerd | Exterior landscapring | Remove oak tree by parking lot |  | 2019 | 2019 |  | Maintenance | Oak tree removed in 2019 | 15 | 5 | 3 |  |  |  | 2000 | 970 | 2018 |  | 515005 - Maint. Grounds |  |  | Done | 2019
Dawes | Tree trimming | Perform routine trimming |  | 2019 | 2019 |  | Maintenance - Trees have several dead branches and overhang house, some branches are rubbing on the roof | some pruning may be possible with volunteers. Plan to be developed | 15 | 3 | 5 |  |  |  | 2000 |  | 2018 |  |  |  |  | Done | 2019
Furlong | Garage door | Replace garage door |  | 2019 | 2019 |  | Beyond Useful Life - Original door, several gaps are present |  | 9 | 3 | 3 |  |  |  | 3000 |  | 2019 |  |  |  |  | Done | 2019
Brainerd | Fellowship room | Repair/Replace movable partitions |  | 2019 | 2019 |  | Maintenance – panels are scoring the floor in several locations | current area of concern has progressed to a point of limited additional damage | 9 | 3 | 3 | [5 empty] | 2019 |  |  |  |  | Done | 2019 | current area of concern has progressed to a point of limited additional damage
Dawes | Windows | Replace windows |  | 2019 | 2019 |  | Beyond Useful Life - Revise based on inspection report; potential for increasing energy efficiency and improved functionality | Windows replaced June 2019 | 9 | 3 | 3 |  |  |  | 10000 |  | 2019 |  |  |  |  | Done | 2019 | Windows replaced June 2019
Brainerd | Exterior | Widen and resurface (new stone) path from parking lot to Cook Street |  | 2019 | 2019 |  | TBD |  | 3 | 1 | 3 |  |  |  | 1200 |  | 2019 |  |  |  |  | Done | 2019
Brainerd | Parking lot/exterior | Replace exterior lights with LED fixtures |  | 2019 | 2019 |  | Increase energy efficiency/reduce maintenance costs for bulb replacement | LEDs have extended lifetime; Replacement of existing incandescent bulbs requires a bucket truck - high cost maintenance item annually Endowment funds being used to do a portion of the lot in 2019 | 1 | 1 | 1 |  |  |  | 5000 |  | 2019 |  |  |  |  | Done | 2019 | LEDs have extended lifetime; Replacement of existing incandescent bulbs requires a bucket truck - high cost maintenance item annually Endowment funds being used to do a portion of the lot in 2019
Brainerd | Kitchenette | Energy efficient refrigerator |  | 2019 | 2019 |  | Improve energy efficiency consistent with Green Team objectives | replaced in 2019 | 1 | 1 | 1 |  |  |  | 1000 |  | 2020 |  |  |  |  | Done | 2019
Furlong | Laundry | Replace washer and dryer |  | 2019 | 2019 |  | Current units are several years old, units are functioning; replace when they stop functioning | Dryer replaced in 2018, washer replaced in 2019 | 1 | 1 | 1 |  |  |  | 600 |  | 2018 |  |  |  |  | Done |  | Dryer replaced in 2018, washer replaced in 2019
Brainerd | Kitchen | Evaluate heat balance during heating season |  | 2019 | 2019 |  | Maintenance - Control system issue, kitchen is excessively warm in winter; this is uncomfortable for those working in the kitchen and also wastes energy | Addressed through installation of new BAS | 9 | 3 | 3 | [5 empty] | 2018 |  |  |  |  | Done |  | Addressed through installation of new BAS
Brainerd | Brainerd entrance | Refinish outside entrance doors | Major Maintenance | 2020 | 2020 |  |  | Gives poor impression, without protection wood will deteriorate further | 15 | 3 | 5 |  |  |  |  | 540 |  |  | 515009 - Maint. Service |  |  | Done | 2020 | Doors painted by Geno Baker
| Grounds | Wind Damage - Retaining Wall | Major Maintenance | 2020 | None |  | Retaining Wall damaged - neighbor says that the wall/ damage is his responsibility as of 10/13/20 | Retaining wall in SW corner of parking lot failed. Looking at replacement with wooden beams or concrete block | 0 |  |  |  | - New quote for around $_________ - We will cover the cost since our tree did the damage and to maintain the relationship with the neighbor - Replacing the entire wall is the recommended option. - Motion for replacement of the retaining wall: Since _____ is the owner motion was: Propose to replace the retaining wall with wood (like for like) either partial or entire section as needed. Award contract to ____. Motion: ___ Second: ___ Unanimous approval. | Can fit in current 2020 budget listed account.
Dawes | Roof | Replace roof | Project | 2019 |  |  | Beyond Useful Life - Roof showing signs of wear, shingles lifting; revise based on inspection report | TO be done 2019 | 9 | 3 | 3 |  |  |  | 21000 | 9563.07 | 2019 |  |  |  |  | Done | 2019 | Completed in 2019 total cost was $9,563.07. Deposit in October 2019 of $4,781.54 and the final payment in December of $4,781.53.
| Exterior | Outdoor lighting timer | Project | 2020 | None | [7 empty] | Lost a timer for outdoor lights on north parking lot. Replace with Digital | Not to exceed $_____. Can fit in current 2020 budget listed account.
Brainerd | Kitchen FH | Door adjustment | Major Maintenance | 2020 | 2020 |  | Maintenance - Door is damaging floor, frame is in concrete block so cannot move | Looking for vendor to service door (Steve March was originally checking, is that still happening?) | 9 | 3 | 3 |  | Remove door and plane end off sufficiently. Chuck to work. |  | ??? |  | 2019 |  |  |  |  | Done
Brainerd | The Grove | Regrade playground area, add soil - "The Grove" Project | Project | 2020 |  |  | Member suggestion of additions to Grove landscaping | Proposal being looked at to see if it meets overall Church needs for use of the Grove area. | 9 | 3 | 3 |  | (Perhaps initial phase of "The Grove" project) |  | 750 | [6 empty] | Done
Brainerd | Assoc. Pastor office | Rewire ceiling lights to enable zone lighting/enable use of dimmer for flexible lighting | Project | 2020 | 2020 |  | Maintenance (separate lights from main office light circuit and control – isolate lighting/control | Desire to have 2 zones with dimmers | 1 | 1 | 1 |  | Have to put new fixtures in to make dimming available. As of Nov 2020 the work is done as much as it will be done. |  | 2270 |  | 2019 |  |  |  |  | Done
Brainerd | Exterior | Church sign letters | Project | 2020 | 2020 |  | Beyond useful life | Endowment funding approved | 16 | 4 | 4 |  | Replace lettering in Church sign that are beginning to fail | Endowment might cover letter replacements also. | 300 | 300 | 2020 |  |  | 300 |  | Done
| Exterior | Repair stone wall in window well | Major Maintenance | 2020 | None |  | Prevent water backup/ intrusion | A few stones from the wall around the basement window well have fallen due to erosion and must be shored up. | 16 | 4 | 4 |  |  | Can fit in current 2020 budget listed account.
Brainerd | Sanctuary | Roof Leak on SE corner | Major Maintenance | 2020 |  |  | Causing wall damage and staining | Leak was found during service filming in June | 25 | 5 | 5 |  | Clean out roof drains and repaint wall |  | ??? | [6 empty] | Done
Brainerd | Exterior landscapring | Replace 3 trees in "Grove" | Project | 2020 | 2020 |  | 3 Trees were removed due to disease, etc. | Replace with trees of choice | 0 |  |  |  | Trustees voted to replace the 3 trees with a Hackberry, a American Sentry Linden, and an American Beech. Trees donated, actual cost was Village of Libertyville permits - $265 and estimate of trees $700 |  | 750 | 265 | 2020 |  | 515005 - Grounds |  |  | Done
| Stairs | Extend handrail | Project | 2020 | None | [7 empty] | Hand rail to be evaluated on Wednesday [date]. Work to be done to extend the handrail on one side of the stairs to the full length of the stairs. _______ to assist with the work. | Can fit in current 2020 budget listed account.
Brainerd | Sanctuary | Parapet surface stablization - Part 1 cap repairs | Project | 2020 |  |  | Cracking in and around parapet | Resource Committee said to move ahead against Special Project #2 fund. | 25 | 5 | 5 |  | Mikway proposal - - Repair concrete caps where weather damage to concrete caps - Tuck point where needed - Clean and repair any open joints in caps and brickwork - 8/3/20 1/2 deposit of $3430 paid to Mikway |  | 5000 | 5860 |  |  | 515003 - Roof |  |  | Done
| Exterior | Soffit and Facia Repair | Major Maintenance | 2020 | None |  |  |  | 0 |  |  |  | "______" proposal from ________ | - 8/11/20 1/2 deposit to _________ roofing for $___. Can fit in current 2020 budget listed account.
| Exterior | Chimney Repair |  | 2020 | None |  |  | Faux chimney and cap replacement due to age. | 0 |  |  |  | Estimate from __________: Tile breaking as needed, removal,and disposal of all materials. Reline fireplace flue with a stainless steel chimney liner from the top of the smoke chamber to the top of the chimney flue. Insulate liner with thermix chimney insulation. Remove existing damper and frame as needed and seal smoke chamber as needed with chambertech high heat mortar. Installation of a 13x13 energy top plus damper and flue tile extension. Tenant being advised not to use as of 12-09-2020 | Does NOT fit in current 2020 budget. Currently being considered "nice to have" but not necessary at present.
Brainerd | Sanctuary | Organ temolo vibrato units | Project | 2020 | 2020 |  | Organ maintenance |  | 16 | 4 | 4 |  | Update/ replace remolo vibrato units |  | 3419 |  | 2020 |  |  | 3419 |  | Done |  | Organ temolo vibrato added from Endowment Funds
Brainerd | Education wing | Eduction wing lighting | Project | 2020 | 2020 |  | Safety and Access |  | 12 | 4 | 3 |  | Update/ replace lighting in eduction wing. . Current sockets are ~50 years old and crumbling. Replacement of the sockets will be a more cost effective alternative and will enable use of 200 w LEDs. |  | 1199 | 1199 | 2020 |  |  | 1199 |  | Done | 2020 | Portion of lighting replaced and fixed
Brainerd | Fellowship hall | Fellowship hall coffee maker | Project | 2020 | 2020 |  | Replacement |  | 6 | 2 | 3 |  | Replace coffee maker in fellowship hall - Elec for new coffee maker $143.75, coffee maker $966.78 |  | 1200 |  | 2020 |  |  | 1110.53 |  | Done
Brainerd | Parking Lot | Parking Lot Seal Coating and Striping | Project | 2020 |  |  | Maintain parking lot | Was to be done in 2019 but deferred due to spending constraints | 0 |  |  |  | Estimated cost is from 2019 and will be honored |  | 3239 | 3239 |  |  | 515023 - Parking Lot |  |  | Done
Brainerd | Exterior | Church sign springs | Project | 2020 | 2020 |  | Beyond useful life |  | 16 | 4 | 4 |  | Replace spring in Church sign that no longer hold the sign cover open for access | Endowment might cover letter replacements also. | 400 | 333.35 | 2020 |  |  | 633.35 |  | Done
Brainerd | Grounds | Wind Damage - Tree | Major Maintenance | 2020 |  |  | Clean up tree limbs/ debris from July 9th 2020 wind storm |  | 0 |  |  |  | Remove and clean-up |  | 400 | 400 |  |  | 515005 - Maint. Grounds |  |  | Done
| Mature trees | Annual maintenance/macro-micronutrient infusions | Major Maintenance | 2021 | 2021 |  | Maintenance - Improve long term health of the trees – delay removal and associated expenses | Included in 2020 budget, but not done in Spring, so moved to 2021 Spring | 25 | 5 | 5 | [5 empty] | 2018
Dawes | Water Heater and Bsmt restoration | Replace due to flooding in May 2020 | Major Maintenance | 2020 |  |  | Basement flood in May | Water heater was damaged due to basement flooding | 0 | [6 empty] | 2723.74 |  |  | 516052 - Dawes Maint. |  |  | Done | 2020 | May 2020 flooding (due to sump pump plug falling out) which resulted in Bsmt restoration/ clean up. Found WH damaged and thus replaced.
Elm Court | Exterior | Sidewalk replacement | Project | 2019 |  |  |  |  | 0 | [12 empty] | Done
Furlong | Roof | Repair eyebrow roof over the front door | Major Maintenance | 2020 |  |  |  |  | 0 | [6 empty] | 1480 |  |  | 516002 - Furlong Maint. |  |  | Done
Brainerd | Community room | Curio cabinets for community room | Project | 2020 | 2020 |  | Improvement/ update |  | 4 | 2 | 2 |  | Add curio cabinets in Community room to display Church related items/ information |  | 2000 | 1183.96 |  |  |  | 1183.96 |  | Done | 2020 | Obtained and put in from Endowment Fund
Brainerd | Senior pastor’s office | Evaluate heating/air conditioning unit performance – evaluate need for replacement | Project | 2020 | 2020 |  | Mitsubishi wall unit installed as stop gap measure, currently working, unit has been cleaned | Now able to get heat from radiator system | 1 | 1 | 1 |  |  |  | 1000 |  | 2020 |  |  |  |  | Done | 2020 | Found to be not required due to valving was replaced enabling heat to be transferred to office.
Van | Church van | Develop long term plan | Project | 2020 | 2020 |  |  | Make decision to replace or rent as needed; cost analysis likely favors not replacing Likely to last another 2 years | 0 |  |  |  | Van use limited to trips <100 miles. No further maint. Other than oil changes to be done. | [8 empty] | Done | 2020 | Voted that Van no longer can be used for trips over 50 miles and cannot be used to pull the Church trailer (small red). Maintance will be limited to oil changes. If any further material maintenance is required, then the Van will be sold or disposed of to avoid further costs to Church.
Brainerd | Restrooms | Freshen up, paint etc | Project | 2020 |  |  |  |  | 9 | 3 | 3 |  | o Net overage due to unexpected drywall repairs – $2600 - Wallpaper was applied originally without sizing the walls – outer layer of drywall removed with the wallpaper requiring significant additional labor to repair the drywall o Original painting – $2300 o Final painting $4900 o New ceiling tiles (volunteer Labor) $1438.65 (Lowe’s) o Total cost $6338.65 |  |  | 6338.65 | [5 empty] | Done
| Exterior landscapring | Remove and replace ash trees | Project | 2021 | 2021 |  | Remove ash trees and oak | Need to determine how to replace the 3 trees and with what type(s) of trees. | 15 | 5 | 3 |  | Oak near dumpster has been removed and two Ash near church to be removed. |  |  |  | 2020
Dawes | Hallway bath sink | Repair or Replace Hallway Sink |  | 2020 |  |  |  | In drastic need of replacement, dual sinks, one has a repaired crack. Should this be done now or wait until Assoc Pastor requirement? | 0 |  |  |  | Completed by sealing (temporary) so fixed for now. | [5 empty] | 516053 - Dawes Improvements |  |  | Done
| Sanctuary | Parapet surface stablization - Part 2 expand membrane | Project | 2021 | SP |  | Expansion of membrane over parapet to fully seal | Resource Committee looking into how to fund as of 8/18/20. Likely not against 2020 Trustee budget accounts. | 25 | 5 | 5 |  | Great Lakes work to Extend current membrane roofing up the full inside height of the parapet wall, annealing the added membrane to the existing membrane Extend membrane over the top of the wall caps and terminate on the outer wall with engineered drip edge with closure system that conceals and protects drip edge anchors. | $______ paid 10/15/20 presumably as deposit to start work if possible in 2020. | [6 empty] | Resource Comm said will fund from "excess funds" so project is against a budget acct and will be overage that is covered.
| Exterior | Basement waterproofing | Project | 2021 | 2021 |  | Leakage could lead to long term damage | 2020 budget item approved by Resource Committee | 16 | 4 | 4 |  | - Waterproofing was included in 2020 at $_______ but still has not been done. $_______ in 2021 budget - Some water is still coming in but not as badly as it has been in the past - Things are improved – this could be an option to install the DIY solution of a surface channel to re-direct the water to the sump pump. Cost would be significantly less. - Mark will provide a summary of the DIY solution to redirect the water | $______in 2021 budget
| FH Kitchen | Annual maintenance program for appliances | Major Maintenance | 2021 | 2021 |  |  | Need to put in annual maintenance program for appliances | 15 | 5 | 3 |  | Repair or replace
| Kitchenette | Replace faucet with removable to enable filling of tall coffee pots/drink coolers | Project | 2021 | SP |  | Improve efficiency/reduce movement of liquids from Kitchen through nave to the community room | Consider replacing in 2019 Chuck to purchase | 3 | 1 | 3 |  | Replace sink faucet with faucet that enables tall coffee pots to be filled in sink, or has a "hose faucet" that enables filling on counter |  |  |  | 2019
| Fellowship Hall | Replace round tables - 2021 phase | Project | 2021 | SP |  | Improvement - Current folding tables are very heavy/difficult to move and showing signs of wear and tear; replace with lighter weight more durable tables; phase in over 3 years | Tables being dragged around damages floor, potential for injury to individuals moving tables. | 9 | 3 | 3 |  | Consideration of phased replacement of tables over 3 years. Cost for 4 tables is approx. $______ with total number to be replaced TBD.
| Mechanical Areas | Storage and Lighting for Mechanical Areas | Project | 2021 | Endow |  | Safety and Access |  | 8 | 2 | 4 |  | Add proper lighting and additional storage in mechanical areas of church building | Endowment 2020 |  |  | 2020 |  |  | 500
| Community room | Community room chairs | Project | 2021 | Endow |  | Improvement/ update | Need to address in 2020 since Endowment funds allocated for this. | 4 | 2 | 2 |  | Need to replace/ add to the Community room chairs | Endowment 2020 |  |  | 2020 |  |  | 1200
| Bathroom | Update bathroom to replace gold tub, toilet and sink | Project | 2021 | None |  | Cosmetic | This would be a fairly major cost project to fully update a very outdated bathroom (early 70s era). Main emphasis if an Assoc. Pastor takes residence. | 1 | 1 | 1 |  | Do when a new Assoc Pastor is expected to come in versus tenant. | Project not in current 2021 budget. Budget Account # shown for informational purposes only. |  |  | 2020
| Kitchen | Update kitchen countertop | Project | 2021 | None |  | Cosmetic | Update of outdated kitchen. Main emphasis if an Assoc. Pastor takes residence. | 1 | 1 | 1 |  | Do when a new Assoc Pastor is expected to come in versus tenant. | Project not in current 2021 budget. Budget Account # shown for informational purposes only. |  |  | 2020
| Laundry | Replace washer and dryer | Project | 2021 | None |  | Current units are several years old, units are functioning; replace when they stop functioning | Not sure of timing, more of a "what if" placeholder item. | 1 | 1 | 1 |  | Do when a new Assoc Pastor is expected to come in versus tenant. | Project not in current 2021 budget. Budget Account # shown for informational purposes only. |  |  | 2020
| Roof | Replace roof | Project | 2021 | None |  | Original roof (1978) | Limited funding available from Ruth Ross gift 2019 inspection did not indicate issues other than need to clean. NOTE: need to determine replacement with Cedar or Architectural Shingles. Neighborhood desires Cedar so could become a "political" issue. Need to also look into better venting in the attic. | 3 | 3 | 1 |  | Need to verify that it needs to be replaced and if so, when? | Project not in current 2021 budget. Budget Account # shown for informational purposes only. |  |  | 2019
| Roof | Vents - powered and fixed | Project | 2021 | None |  |  | Determine if can add powered attic exhaust fan and possibly increased roof edge vents |  |  |  |  | _______ has proposal from ________ | Project not in current 2021 budget. Budget Account # shown for informational purposes only.
| General | New Digital Keyboard | Project | 2021 | 2021 | [7 empty] |  New digital keyboard (______), estimated cost of $______ • Could consider endowment • Will add to 515007 Sound System along with $______ included in the 2020 budget to cover cost of replacing bulbs and potential for other smaller expenses
| Parking Lot | Parking lot maintenance – seal coating and striping | Major Maintenance | 2021 | 2021 | [7 empty] | Crack sealing needed in 2021 since they did not do a very good job on crack sealing this year. Next coating due in 2022 since done in 2020.
| HVAC | Gate Valve Replacements | Project | 2021 | None | [7 empty] | To replace leaking and broken valves Re-use existing pumps Rework piping Reinsulate new piping | Project not in current 2021 budget. Budget Account # shown for informational purposes only.
| HVAC | UV Air Purification system | Project | 2021 | None | [7 empty] | Install 1 to 7 UV air purification systems | Project not in current 2021 budget. Budget Account # shown for informational purposes only.
| HVAC | Community Room Roof Top Unit Replacement | Project | 2021 | None | [7 empty] | Install new Carrier 7-1/2 ton unit | Project not in current 2021 budget. Budget Account # shown for informational purposes only.
| HVAC | Balancer for Sanctuary Air Handler | Project | 2021 | None | [8 empty] | Project not in current 2021 budget. Budget Account # shown for informational purposes only. | ???
Brainerd | Fellowship Hall | Replace round tables - 2022 phase | Project | 2022 | None |  | Improvement - Current folding tables are very heavy/difficult to move and showing signs of wear and tear; replace with lighter weight more durable tables; phase in over 3 years | Tables being dragged around damages floor, potential for injury to individuals moving tables. | 9 | 3 | 3 |  | Consideration of phased replacement of tables over 3 years. Cost for 4 tables is approx. $900 with total number to be replaced TBD. |  | 900 |  |  |  | 515026 - Special Proj #2
Furlong | Windows | Replace remaining original windows | Project | 2022 | None |  | Improve functionality and energy efficiency | Need to inventory the number that remain to be replaced and obtain estimates. | 3 | 3 | 1 |  |  |  | 10000 |  |  |  | 516003 - Fulong Improvements
Brainerd | Room 206 | Update lighting to specification of youth program/band | Project | 2022 | None |  | Request from youth pastor | AV, lighting, staging, flooring Work can be staged Mark working with Gonzo to plan Look for alternate funding | 15 | 5 | 3 |  |  |  | 14000 |  | 2019
Brainerd | Education wing | Window AC units | Project | 2022 | None |  | Evaluate need to replace; units are currently functional and have been cleaned; continue with regular maintenance | plan for phased replacement to prevent simultaneous failure of multiple systems | 3 | 3 | 1 |  | Approx. $600 each unit. Assume about 8 units? |  | 4800 |  | 2019
Brainerd | Fellowship Hall | Air conditioning system | Project | 2022 | None |  | Long range plan Need to determine age of unit, impact of changes to control system associated with new boiler | Evaluate serviceable life of air conditioning system – develop long range plan for replacement | 5 | 5 | 1 |  |  |  | 20000 |  | 2020
Brainerd | Fellowship Hall | Replace round tables - 2023 phase | Project | 2023 | None |  | Improvement - Current folding tables are very heavy/difficult to move and showing signs of wear and tear; replace with lighter weight more durable tables; phase in over 3 years | Tables being dragged around damages floor, potential for injury to individuals moving tables. | 9 | 3 | 3 |  | Consideration of phased replacement of tables over 3 years. Cost for 4 tables is approx. $900 with total number to be replaced TBD. |  | 900 |  |  |  | 515026 - Special Proj #2
Elm Court | Roof | Replace roof | Project | 2023 | None |  | Beyond Useful Life - just completed some repairs to address issues; assess need for further repairs or replacement | Review inspection report, portion replaced in 2018 | 9 | 3 | 3 |  | Determine if and when needs to be replaced. |  | 15000 |  | 2018
Elm Court | Boiler | Replace boiler | Project | 2023 | None |  | Beyond useful life - Currently working; replacement could provide option to remove chimney and enlarge room upstairs | Based on maintenance in 2019, need for replacement could be later | 9 | 3 | 3 |  | 5000 (does not include cost of removing chimney) |  | 5000 |  | 2020
Brainerd | Office | Enable dimmer for lights over secretary's desk | Project |  | None |  | Request from Melinda | probability to handle under maintenance budget in 2019 | 1 | 1 | 1 |  | Warm Glow LED lighting and dimmers |  | 700
Dawes | Sump pump | Repair and fix drainage | Major Maintenance |  | None |  | Basement flood in May 2020 | Found electrical plug to sump pump had fallen out and drain line partially plugged | 25 | 5 | 5 |  |  |  | ???
Elm Court | Exterior | backyard interaction space | Project |  | None |  | Provide area for more private gatherings | Not able to put paved system since need water percolation to prevent flooding. To add a deck would be very challenging due to area and grade up/down from house access. | 1 | 1 | 1 |  |  |  | 7000 |  | 2020 |  | 516073 - Elm Ct Improvements
Furlong | Front Entrance | Replace front door and sidelights | Major Maintenance |  | None |  | One sidelight is cracked-look into repair options | Major review of the situation to determine long term solution. Could require total replacement of double door and sidelights. | 1 | 1 | 1 |  |  |  | 5000 |  | 2018 - repair sidelight/2020 plan |  | 516002 - Furlong Maint.
Furlong | Fireplace | Convert to gas log fireplace | Project |  | None |  | Preference to convert from wood to gas | Chuck to get bid. Apparently gas is adjacent. | 1 | 1 | 1 |  |  |  | 1000 |  | 2020 |  | 516003 - Fulong Improvements
Brainerd | Interior doors | Refinish interior doors Audit doors and identify repair needs; some sweeps need repair, some doors don't close completely | Project |  | None |  | Maintenance, impact to functionality, need to be cleaned as well. | Plane as needed to eliminate sticking | 3 | 3 | 1 | [5 empty] | 2018/2019
Furlong | Water Heater | Replace | Project |  | None |  |  | Replace next time service is needed | 15 | 5 | 3
Brainerd | Wireless PA system | Recommended as part of active shooter initiative | Project |  | None |  |  |  | 9 | 3 | 3
Brainerd | Fellowship Hall | Mullion between external doors needs to be replaced due to rust/corrosion | Major Maintenance |  | None |  | Removable "post" between doors is rusted and cannot be removed. |  | 3 | 3 | 1
Brainerd | Fellowship Hall | Window treatments | Project |  | None |  |  |  | 3 | 1 | 3
Dawes | Garage Floor | Evaluate and repair floor | Project |  | None |  | Concrete pitted but usable | At best consider epoxy coating | 3 | 3 | 1
Brainerd | Parking lot timers | Replace existing timer with automated system | Project |  | None |  | Eliminate need to manually update timers; provides lighting as needed | Timers are difficult to adjust manually and require frequent adjustment. Evaluate combining with current control system? | 1 | 1 | 1
Brainerd | Brainerd entrance | Replace cracked glass | Major Maintenance |  | None |  | Unsightly but hard to detect normally. | Cosmetic - window above double doors cracks when expands. | 1 | 1 | 1
Brainerd | Room 206 | Chair cart | Project |  | None |  |  | If obtained, where would this be stored? | 0
Dawes | Landscape | Develop plan | Project |  | None |  |  |  | 0
Furlong | Landscape | Develop plan | Project |  | None |  |  |  | 0
Brainerd | Landscape | Develop plan | Project |  | None |  |  |  | 0
Dawes | Sidewalk/driveway | Look at replacing | Project |  | None |  | Curb appeal and sidewalk very close to house. This is the sidewalk from garage to home. | Could be incorporated in landscaping but at present is not a hazard or in need of repair. | 0 | [5 empty] | 10000
Brainerd | Overall | Electrical Panel Replacement | Project |  | None |  | Panel has reached capacity and has been "modified" for an addtitional circuit | The issue is back in 2011, during the capital campaign to add an elevator, major work to the foundation in the fellowship hall and other building corrections, a new circuit was installed that required the panel board be modified to fit the current available fuse breaker. A member of the solar group, a retired electrical engineer, was viewing the panel during a meeting and planning session by the solar task force and took exception to the reworked panel design. We have had a number of electrical professionals look at the panel with all saying that it should be replaced at some point but none thinking that it posed an immediate threat to the building. NOTE: desire is to determine if solar is going in to upgrade panel once not twice. | 9 | 3 | 3 |  | Estimates received to date: Cahill Electric = $14,550.00 Krause Electric = $17,350.00 Hucker Electric = $21,366.00 |  | 21366
Brainerd | HVAC | Room 100 & 200 Zoning Valve Additions | Project |  | None | [7 empty] | Currently these room have no way to regulate the heat Need to survey the structure and develop a plan Survey would take 2 men one day |  | 1950
Brainerd | Exterior | Oak wood slabs |  | 2022 | [8 empty] | Reminder of use of oak wood slabs. Target "cure" is 2022.
| Kitchen | Freezer replacement | Project | 2021 | None | [8 empty] | Project not in current 2021 budget. Budget Account # shown for informational purposes only.

## Budget
Accounts | 2020 Budget | 2020 YTD | 2021 Proposed | 2021 Budget | 0
Church
XXXXXX - Heat & Air Cond Contract Svcs Chur
XXXXXX- Heat & Air Cond REPAIRS - Church
XXXXXX - Roof Contract Svcs & Repairs - Chur
XXXXXX - Grounds - Church
XXXXXX - Insurance - Church
XXXXXX - Maintenance - Sound System - Church
XXXXXX - Maintenance - Music Eqpmt - Church
XXXXXX - Maint. Service/Repairs - Church
XXXXXX - Maintenance Contracts - Church
XXXXXX - Kitchen Supplies
XXXXXX - Custodial Supplies
XXXXXX - Maint. Contracts - Security/Fire
XXXXXX- Utilities - Gas - Church
XXXXXX - Utilities - Electric - Church
XXXXXX- Utilities - Miscellaneous - Church
XXXXXX Projects (Non-Capital Expense) |  |  |  |  | 0
XXXXXX - Elevator Maint/Service
XXXXXX - Parking Lot Maint/Service
XXXXXX- BAS Contract Svcs & Repairs
XXXXXX - Trustee Special Project #2 |  |  |  |  | 0
XXXXXX- Misc/All Other Maint - Church |  |  |  |  | 0
XXXXXX - Requested New Acount for Improvements
Contract Services
XXXXXX - Custodial Cleaning of Church-Other
XXXXXX - Snow Removal - Church
XXXXXX - Custodial Cleaning Church-Weekly
Total Church | 0 | 0 | 0 | 0
Parsonage
Senior Pastors - Furlong Parsonage
XXXXXX - Utilities - Gas - Sr Parsonage
XXXXXX - Maintenance - Sr Parsonage |  |  |  |  | 0
XXXXXX - Improvements - Sr Parsonage |  |  |  |  | 0
XXXXXX - Utilities - Electric - Sr Parsonage
XXXXXX - Utilities - Misc - Sr Parsonage
XXXXXX - Lawn Care/Snow Rmvl-Fulong Prsng
Total Senior Pastors - Parsonage | 0 | 0 | 0 | 0
Associate Pastors - Dawes Parsonage
XXXXXX - Utilities - Gas - Assoc Parsonage
XXXXXX - Maintenance - Associate Parsonage |  |  |  |  | 0
XXXXXX - Improvements |  |  |  |  | 0
XXXXXX - Utilities - Elec - Assoc Parsonage
XXXXXX- Utilities - Misc - Assoc Parsonage
XXXXXX - Real Estate Taxes - Dawes Property
XXXXXX - Lawn Care/Snow Rmvl-Dawes Prsng
Total Associate Pastors - Parsonage | 0 | 0 | 0 | 0
Other Properties - Elm Court
XXXXXX - Utilities - Misc - Elm Ct Property
XXXXXX - Maintenance - Elm Ct Property |  |  |  |  | 0
XXXXXX - Improvements - Elm Ct Property |  |  |  |  | 0
XXXXXX - Utilities - Elec - Elm Ct Property
XXXXXX - Utilities - Gas - Elm Ct Property
XXXXXX - Utilities - Cable - Elm Ct Property
Total Youth Paster - Parsonage | 0 | 0 | 0 | 0
Church Vehicles
XXXXXX- Maintenance - Van
XXXXXX - I-Pass - Van
Total Church Vehicles | 0 | 0 | 0 | 0
Total Building & Maintenance | 0 | 0 | 0 | 0

## Definitions
Risk | Value | Definition
High | 5 | life-safety issue, continuing maintenance issues and costs associated with periodic failures of existing item
Medium | 3 | Item currently showing significant signs of wear, greater than 5 years beyond expected useful life, however, no current signs of failure
Low | 1 | Optional improvement to enhance delivery of programs, replacement of existing item with lower maintenance or greener alternative; cosmetic improvement of facility
Urgency
High | 5 | Failing system or facility that cannot meet the needs of current programs. Maintenance or replacement needed within 3-9 months
Medium | 3 | Improvement can be deferred with no life-safety impact, limited impact on delivery of programs but which require some work-arounds to enable delivery; can be deferred for 12-24 months with limited impact
low | 1 | No life-safety impact, action can be deferrred for more than 24 months with limited impact to programs.